# COURT INTELLIGENCE MANAGEMENT SYSTEM

IMPLEMENTATION PLAN DAN TATA KELOLA PENGEMBANGAN

Rencana kerja setelah baseline proses dan sebelum pembangunan modul jadwal serta ruang sidang virtual

| Item | Keterangan |
| --- | --- |
| Kode Dokumen | CIMS-IMP-005/2026 |
| Versi | 1.0 |
| Status | Implementation Readiness Baseline |
| Tanggal | Juli 2026 |
| Sumber Baseline | SOP Revisi, BPMN, BRD, ERD, SRS, PKS lintas instansi, dan SEMA Nomor 2 Tahun 2026 |

Dokumen ini merupakan rancangan teknis awal. Implementasi produksi tetap memerlukan persetujuan Product Owner, process owner, unit hukum, keamanan informasi, dan pejabat yang berwenang pada setiap instansi.

# 1. Tujuan

Dokumen ini menetapkan urutan kerja, tata kelola, tim, gate, sprint, lingkungan, dan keluaran yang harus tersedia sebelum CIMS digunakan dalam pilot lintas instansi. Fokus awal adalah Compliance MVP, terutama determination gate, jadwal, pemberitahuan, readiness, ruang sidang virtual, insiden, dan audit.

# 2. Prinsip Pelaksanaan

Compliance-first. Kewenangan manusia, penetapan hakim, pemberitahuan resmi, readiness, dan audit didahulukan sebelum otomasi lanjutan.

Reference-first. CIMS menyimpan referensi terhadap sistem resmi dan tidak membentuk register hukum tandingan.

Human approval. Rekomendasi jadwal, pembuatan ruang, skors, penundaan, dan penutupan tetap memerlukan tindakan pengguna berwenang.

Provider-agnostic. Penyedia konferensi video diakses melalui adapter, bukan ditanam langsung ke logika domain.

Security and privacy by design. Hak akses, data minimization, encryption, masking, audit, dan retention diterapkan sejak sprint awal.

Traceable delivery. Setiap backlog harus dapat ditelusuri ke BRD, SRS, ERD, BPMN, acceptance criteria, dan UAT.

# 3. Tata Kelola Proyek

| Forum | Anggota Minimum | Mandat |
| --- | --- | --- |
| Steering Committee | Pejabat berwenang lintas instansi | Arah strategis, keputusan lintas instansi, anggaran, penerimaan risiko tinggi |
| Product Council | Product Owner Pengadilan, Kejaksaan, Pemasyarakatan | Prioritas backlog, keputusan scope, penerimaan hasil sprint |
| Process and Legal Board | Process owner dan unit hukum | Validasi alur, kewenangan, pemberitahuan, dokumen, dan perubahan regulasi |
| Architecture and Security Board | Architect, DBA, Security, Privacy, DevOps | Architecture decision, threat model, data classification, integration, dan release gate |
| Delivery Team | PM, BA, SA, UX, Developer, QA, DevOps | Desain, pembangunan, pengujian, dokumentasi, dan demonstrasi sprint |
| Pilot Operations Team | Pejabat penghubung, helpdesk, operator TI | Walkthrough, UAT, pelatihan, dukungan pilot, dan evaluasi operasional |

# 4. Development Gate

| Gate | Nama | Kriteria Keluar | Penyetuju |
| --- | --- | --- | --- |
| G0 | Legal and Process Baseline | SOP, BPMN, RACI, batas integrasi, dan klasifikasi data disetujui | Steering Committee |
| G1 | Product Baseline | BRD, KPI, scope, business rules, backlog, dan prioritas disetujui | Product Council |
| G2 | Technical Baseline | ERD, SRS, API contract, provider contract, threat model, test plan, dan migration baseline selesai | Architecture and Security Board |
| G3 | Sprint Ready | Prototype alur, DoR, environment, mock service, seed data, dan acceptance criteria tersedia | Product Owner dan Delivery Lead |
| G4 | Release Candidate | Functional, contract, security, performance, resilience, accessibility, dan UAT internal lulus | QA Lead dan Security Lead |
| G5 | Pilot Ready | UAT lintas instansi, pelatihan, SOP operasional, support, DR drill, dan approval go-live tersedia | Steering Committee |

# 5. Work Breakdown Structure

| WBS | Area | Keluaran |
| --- | --- | --- |
| 1 | Governance and Baseline | Approval, change control, RACI, data owner, risk owner, ADR |
| 2 | Platform Foundation | Repository, CI/CD, environment, observability, secret manager, IAM integration |
| 3 | Identity and Organization | MFA, RBAC, ABAC, delegation, privileged access |
| 4 | Case Reference and Determination | Case reference, sync metadata, electronic request, judicial determination, hard gate |
| 5 | Scheduling | Availability, constraints, conflict engine, proposal, approval, versioning, reschedule |
| 6 | Notice and Acknowledgment | Official notice, delivery proof, acknowledgment, retry, fallback, escalation |
| 7 | Readiness and Verification | Checklist, evidence, technical test, identity, room inspection, private consultation |
| 8 | Virtual Hearing | Provider adapter, provisioning, room template, join token, waiting room, controls, webhook |
| 9 | Hearing Operations | Attendance, hearing events, suspend, resume, postpone, complete |
| 10 | Incident and Continuity | Technical incident, cyber incident, force majeure, custody transfer, fallback provider |
| 11 | Appeal Decision and Records | Notice chain, presence, excerpt, transmission, cassation deadline, official reference |
| 12 | Audit, Monitoring, and Pilot | Immutable audit, compliance dashboard, UAT, training, DR, security assessment |

# 6. Roadmap Sprint Usulan

| Sprint | Durasi | Fokus | Keluaran Minimum |
| --- | --- | --- | --- |
| Sprint 0 | 2 minggu | Foundation and Governance | Repo, CI/CD, environments, ADR, coding standard, data classification, seed strategy |
| Sprint 1 | 2 minggu | IAM and Organization | SSO or login, MFA, role, permission, organization, assignment, delegation |
| Sprint 2 | 2 minggu | Case Reference and Determination | Case reference, request, determination, official reference, hard gate |
| Sprint 3 | 2 minggu | Scheduling Core | Availability, constraint, proposal, conflict check, explainability |
| Sprint 4 | 2 minggu | Scheduling Approval and Versioning | Approval, active schedule, reschedule, token invalidation event, audit |
| Sprint 5 | 2 minggu | Notice and Acknowledgment | Notice chain, delivery attempt, proof, acknowledgment, retry and fallback |
| Sprint 6 | 2 minggu | Readiness and Verification | Checklist, technical test, identity verification, room inspection, READY gate |
| Sprint 7 | 2 minggu | Provider Adapter and Session | Provider mock, provisioning, room template, health, webhook validation |
| Sprint 8 | 2 minggu | Join and Hearing Control | Token, waiting room, role control, consultation room, attendance, hearing state |
| Sprint 9 | 2 minggu | Incident and Continuity | Technical, cyber, force majeure, provider fallback, custody transfer |
| Sprint 10 | 2 minggu | Appeal Decision Workflow | Decision reading, notice chain, presence, excerpt, transmission, deadline |
| Sprint 11 | 2 minggu | Audit, Dashboard, Reconciliation | Immutable audit, compliance metrics, source reconciliation, reports |
| Sprint 12 | 2 minggu | Hardening and Pilot UAT | Security, performance, resilience, accessibility, training, UAT, release package |

# 7. Tim Minimum dan Akuntabilitas

| Peran | Jumlah Minimum | Tanggung Jawab |
| --- | --- | --- |
| Product Owner lintas instansi | 3 orang | Prioritas, acceptance, keputusan scope, dan koordinasi process owner |
| Project Manager atau Delivery Lead | 1 | Timeline, dependency, risk, budget, dan communication plan |
| Business or System Analyst | 2 | Backlog, traceability, process, data, API, dan acceptance criteria |
| Software Architect | 1 | Modular architecture, integration, ADR, performance, dan technical gate |
| Backend Engineer | 3 | Domain service, API, data, outbox, integration adapter |
| Frontend Engineer | 2 | Web workflow, accessibility, role-based UI, dashboard |
| QA Engineer | 2 | Automation, contract, E2E, UAT, defect management |
| DevOps or SRE | 1 | Environment, CI/CD, observability, backup, DR, release |
| Security Engineer | 1 | Threat model, secure design, testing, incident readiness |
| UX Designer | 1 | Prototype, usability, accessibility, design system |
| DBA or Data Engineer | 1 paruh waktu | Schema, migration, index, retention, reconciliation |

# 8. Lingkungan dan Strategi Branching

| Lingkungan | Tujuan | Kontrol |
| --- | --- | --- |
| LOCAL | Pengembangan individu | Synthetic data, local secret, provider mock |
| DEV | Integrasi harian | Automated deploy, test identity, mock notification and video |
| SIT | System Integration Test | Contract test, official adapter sandbox, performance baseline |
| UAT | Uji lintas instansi | Masked or synthetic data, controlled user, evidence collection |
| PILOT | Operasi terbatas | Approved integration, production-like monitoring, support rota |
| PRODUCTION | Operasi resmi | Formal release approval, DR, SIEM, backup, legal and security controls |

Gunakan trunk-based development atau short-lived branch dengan pull request wajib.

Build harus reproducible, dependency dikunci, dan artifact ditandatangani.

Database migration berjalan satu arah dan memiliki rollback atau forward-fix plan.

Credential produksi tidak boleh tersedia pada developer workstation atau log CI.

Setiap release menghasilkan software bill of materials, change log, test evidence, dan approval record.

# 9. Definition of Ready

Story mempunyai business value, owner, priority, source requirement, dan scope yang jelas.

Acceptance criteria dapat diuji dan mencakup positive, negative, authorization, audit, serta error behavior.

Entity, API, event, permission, dan dependency telah diidentifikasi.

Data classification, privacy impact, dan retention telah dinilai.

Prototype atau contoh alur tersedia untuk workflow yang melibatkan pengguna.

Test data, mock, feature flag, dan observability requirement tersedia.

Tidak terdapat keputusan hukum atau kewenangan yang didelegasikan ke sistem tanpa dasar.

# 10. Definition of Done

Code review, static analysis, unit test, integration test, contract test, dan relevant E2E test lulus.

Authorization, audit, error model, idempotency, correlation ID, dan state transition telah diuji.

API specification, migration, runbook, test evidence, dan user help diperbarui.

Security finding kritis dan tinggi telah ditutup atau diterima secara formal oleh risk owner.

Tidak ada data sensitif, credential, token, atau host secret pada log dan response yang tidak berwenang.

Product Owner menerima demonstrasi dan QA menandatangani acceptance evidence.

Fitur dapat dimatikan melalui feature flag atau rollback plan tersedia untuk perubahan berisiko.

# 11. Change Control

Change request dibuat dengan alasan, dampak proses, dampak hukum, keamanan, data, biaya, dan jadwal.

Business Analyst memperbarui traceability dari SOP sampai UAT.

Perubahan kewenangan, data sensitif, recording, provider, atau AI wajib direview Process and Legal Board serta Architecture and Security Board.

Product Council memutuskan approve, defer, reject, atau emergency change.

Perubahan yang diterima menghasilkan versi baseline baru dan release note.

# 12. Checklist Kickoff Development

| Item | Status Awal | Owner |
| --- | --- | --- |
| Product Owner tiga instansi ditetapkan | Belum | Steering Committee |
| BPMN, BRD, ERD, dan SRS disetujui | Belum | Product Council |
| API dan provider adapter contract disetujui | Disiapkan dalam paket ini | Architect |
| Threat model dan data classification direview | Disiapkan dalam paket ini | Security Lead |
| Test plan dan UAT owner disetujui | Disiapkan dalam paket ini | QA Lead |
| Backlog Sprint 0 sampai 3 memenuhi DoR | Disiapkan dalam workbook | Delivery Lead |
| Environment DEV dan SIT tersedia | Belum | DevOps |
| Identity provider sandbox dan test account tersedia | Belum | IAM Owner |
| Notification and video provider sandbox tersedia | Belum | Integration Owner |
| Pilot unit, data scenario, support rota, dan training plan ditetapkan | Belum | Pilot Operations Team |

# 13. Keluaran Tahap Berikutnya

Prototype UI yang mencakup determination, schedule proposal, conflict, notice, readiness, dan waiting room.

Repository skeleton untuk backend, frontend, infrastructure, contract test, dan database migration.

Mock provider untuk notification gateway, official case adapter, identity provider, dan video provider.

Sprint 0 kickoff, architecture walkthrough, security workshop, dan test data workshop.

Pilot charter dan criteria go or no-go.